## Cover
QA Report
Sprint | : | 1
Project | : | DRIVER
Build | : | 1.0.0
Date | : | 2023-09-25
Reporter | : | Sheikh Md. Rezone Ullah

## Release Summary
Driver Release Summary Report
Release Info |  | Browser & Device List
Release Name | WK-1 | # | Device Name | Desktop web Browser | Version
Version Name | V-1.0.0 | 1 | PC(Windows) | Windows 10 or above - Chrome | Chrome Version 117.0.5938.89
Release Topic | 1.Login 2. Dashboard 3.My Account 4.Manage Duplicate Record 5.Map 6.Record List 7.Add a Record.
Start Date | 25-09-2023
End Date | 27-09-2023
QA Release Date | 27-09-2023
Release Status | N/A
Released By | Sheikh Md. Rezone Ullah
Prepared By | Sheikh Md. Rezone Ullah
Verified By | Abdul Qadir
Executed Test Type:
1 | Functional test
2 | UI test
Non Executed Test Type:
1 | Regression
2 | Security
3 | Virus Checking
4 | Reliability
5 | Usability
6 | Performance
7 | Device compatibility

## Functionality Verification
DRIVER Release Checklist
# | Module | TL Confirmation | Verified by QA | Status (by QA) | TL Comment | QA Comment
1 | Login | Yes | Yes | OK
2 | Dashboard | Yes | Yes | NG |  | #479785 #479783
3 | My Account | Yes | Yes | OK
4 | Manage Duplicate Record | Yes | Yes | NG |  | #479579
5 | Map | Yes | Yes | NG |  | #479592
6 | Record List | Yes | Yes | OK
7 | Add a Record | Yes | Yes | NG |  | #479787
[N.B: We have checked all screens and found some major and minor issues, these are posted in Redmine]

## Graphical Report
DRIVER Test Case Execution Report
| Build Version No: | 1.0.0
| Total Test cases: | 141
| Test Environments (Browsers): | 1
| Total Executable test cases: | 141
| Test Cases Executed: | 138
| Passed: | 132
| Failed: | 6
| NE: | 0
| NA: | 4
| WIP: | 0
| Total Reported Bugs : | 141
| New | 141
| Rejected | 0
| Deferred | 0
| Duplicate | 0
| Assigned | 0
| Open | 0
| Fixed | 0
| Retest | 0
| Verified | 0
| Re-open | 0
| Closed | 0
| Blocker | 0
| Critical | 0
| Major | 1
| Minor | 5
| Trivial | 0
| Total: | 6
| Reported Bugs : (All Sprints) | 6
| New | 6
| Rejected | 0
| Deferred | 0
| Duplicate | 0
| Assigned | 0
| Open | 0
| Fixed | 0
| Retest | 0
| Verified | 0
| Re-open | 0
| Closed | 0
| Low | 5
| Medium | 0
| High | 1
| Urgent | 0
| Immediate | 0
| Total: | 6
Step-2: Sprint#1 Bug summary
Step-2: Sprint#1 Bugs Severity:
Total Bug summary
Total Bugs (Priority wise):

## Bug_list
DRIVER Bug List (WK-1)
Bug Type | Quantity
UI: | 3
Functional: | 3
Total: | 6
# | Bug ID | Bug Summary | Status | Priority | Severity
1 | https://redmine.bjitgroup.com/redmine/issues/479783 | No black spots were found [Black Spots by Severity ] on the Map in the Dashboard. | New | Low | Minor
2 | https://redmine.bjitgroup.com/redmine/issues/479785 | No blue spots were found in Incidents: Last Two Weeks on the Map in the Dashboard | New | Low | Minor
3 | https://redmine.bjitgroup.com/redmine/issues/479787 | Number is auto-shown in ARF Details. | New | Low | Minor
# | Bug ID | Bug Summary | Status | Priority | Severity
1 | https://redmine.bjitgroup.com/redmine/issues/479579 | In the Manage Duplicate Records module, no data record list has been found. | New | High | Major
2 | https://redmine.bjitgroup.com/redmine/issues/479592 | After clicking on the Blackspots button Blackspot does not appear on the MAP. | New | Low | Minor
3 | https://redmine.bjitgroup.com/redmine/issues/479780 | The image is not removed in LOCATION SKETCH after editing in RCF details. | New | Low | Minor
Functional Bugs:
Step-2: Sprint#3- Bug summary
UI Bugs:

## Bug_trend
Sprint | Test case | Bugs | Resolved | Trend
Sprint#1 | 141 | 6 | 0 | 0

## Defect density
Sprint | Effort | Defect | Defect density | Defect density
Sprint#1 | 24 | 6 | 25% | 25%